## Sheet1
#Defining “precalculation” as just the functionality needed to suggest ACMG scores (remaining VISta functionality referred to as Additional VISta [Code/Functionality])
#Need to decide for which data sources the effort required to update won't be worth it
Source table prep or code | Sub-area | Task / Functionality of code needed | Time estimation in days | Status
Source table prep | Gene-phenotype information table | Overseeing manually curated disease-relevant transcript, disease allele frequency cutoff, inheritance pattern, can BS1 be applied (age of onset + penetrance)?, hotspot(PM1)-valid locations/patterns, and valid disease variant types (missense only/LOF only/any) Once AF cutoffs are decided we should QC by comparing to known pathos and specifically the MVL, plot distribution of AFs for each gene's pathogenic variants | 1 | Manually curated results far off. Have Gene-transcript from MVL and HGMD
Source table prep | gnomAD coverage file | Prep for tabix usage (If we have concerns about data size storage, probably can be condensed into a reduced .bed format, collapse intervals with the same coverage, or limit to exons +100bp) | 1 | basically done but not in proj_VISta
Source table prep | HGVD (~1000 exomes) | Multi-allelic sites if any need to be split into one variant per row Left normalize and generate vkey What % of sites are covered >20x on average? Remove sites below or remove individuals below and recalc AF? How many variants exist at an AF greater than observed in gnomAD? >1%? >5%? Convert to db format (tabix ready) | 3 | Done
Source table prep | UK10K | Multi-allelic sites if any need to be split into one variant per row Left normalize and generate vkey What % of sites are covered >20x on average? Remove sites below or remove individuals below and recalc AF? How many variants exist at an AF greater than observed in gnomAD? >1%? >5%? Convert to db format (tabix ready) | 3 | Done
Source table prep | Qatar sequencing study (~1000 exomes) | The three files need to be merged and data adjusted accordingly Multi-allelic sites need to be split into one variant per row Left normalize and generate vkey What % of sites are covered >20x on average? Remove sites below or remove individuals below and recalc AF? How many variants exist at an AF greater than observed in gnomAD? >1%? >5%? Convert to db format (tabix ready) | 3 | Zach's to-do
Source table prep | Sema4's MVL | Remove duplicates?, lift old transcripts to current, resolve any remaining vkey addition issues, compare to pt VCFs? Any work done needs a script to be reran on the most current MVL dump directly preceding VISta usage Finalize upload to VISta | 3 | Zach's priority
Source table prep | Emory's EmVClass | add vkey | 1 | basically done but not in proj_VISta Dianwei to-do
Source table prep | deafness variation database | add vkey | 1 | Done
Source table prep | CFTR france (875) | Copy-paste of nine pages or so (show 100 variants/page), more TBD after copy-paste (add vkey...) https://cftr.iurc.montp.inserm.fr/cgi-bin/variants.cgi?type=all& | 1 | Dianwei to-do
Source table prep | CFTR2 (326) | add vkey | 1
Source table prep | F11 | Needs to be parsed into table (currently quite messy), and vkey | 2
Source table prep | F9 | Needs to be parsed into table with one variant per row maintaining the order of patients, publications, and phenotype/functional information, and vkey added | 2
Source table prep | Infevers db | add vkey | 1
Source table prep | PAH db | Needs to be parsed into table (currently quite messy), and vkey | 2
Source table prep | ALPL db | add vkey | 1
Source table prep | ATP7B db | merge references table, add vkey | 1
Source table prep | COL7A1 db | convert data by patient to data by variant, maintain numbers, add vkey | 2
Source table prep | rmsk | parse and upload to db2 | 1
Source table prep | refGene | Finalize transcript table: 1 table with all transcript data present for searching (with date of most recent refGene table that was merged) Scripts to add version info to a new refGene download and then resolve duplicate alignments after appending new data | 2 | Done
Source table prep | dbscSNV | add vkey | 1 | basically done but not in proj_VISta
Source table prep | dbNSFP | Compare, assess, determine cutoffs for REVEL, CADD, metaSVM vs SIFT, PolyPhen2, MutationTaster2 Consider including VEST3, REVEL, MetaSVM, MutationTaster, Mcap, and CADD (best 6 from Rong email [Plon]) | 7 | basically done but not in proj_VISta
Source table prep | multiz100way | Parse into table with one human interval per row and each possible species's sequence is a column, if a species is not present in the interval note as NA or null, if all gaps note all gaps Is there ever more than one alignment for a single hg19 position? (multi gene/transcript?) How are gaps between human intervals indicated in these files? | 2 | basically done but not in proj_VISta
Source table prep | AA sub matrix (grantham / blossum ) | Compare, assess, determine substitution cutoffs for neutral vs damaging (maybe compare to our pathogenic missense variant db) | 7 | Zach's to-do
Source table prep | uniprot | Need update from Nick - TBD dependent on form of downloaded data |  | Zach's to-do
Precalc functionality | Population data | get_highest_MAF I: vkey O: highest subpopulation/ethnicity MAF with AN > 2000, only 0% if cov>20x/sample | 1
Precalc functionality | Population data | is_pos_covered I: chrom, pos O: Is the position covered > 20x/sample on average? (yes or no) | 1
Precalc functionality | Population data | suggest_BA1_BS1_PM2 I: chrom, pos, vkey, transcript O: BA1, BS1, PM2, or NA if the position is not covered sufficiently | 1
Precalc functionality | Population data | get_total_genotype_counts I: vkey O: Total genotype counts at this position (number homoz, hetero, hemiz) | 1
Precalc functionality | Population data | suggest_BS2 I: chrom, vkey O: BS2 or other options | 1
Precalc functionality | Pathogenic variant database | suggest_PP5_BP6 I: vkey O: PP5, BP6, or other options (concordant assertions, no publication references, not in MVL, compare get_patho to get_patho_MVL) | 1
Precalc functionality | Pathogenic variant database | get_pathogenic_variant I: vkey O: Variant info from pathogenic dbs with a pathogenic assertion (allow discordant for review purposes) | 1
Precalc functionality | Pathogenic variant database | get_pathogenic_variant_MVL I: vkey O: Variant info from MVL | 1
Precalc functionality | Pathogenic variant database | suggest_PS4 I: vkey, transcript O: PS4-M, PS4-P, or other options | 1
Precalc functionality | Pathogenic variant database | get_pathogenic_variants I: chr, start, stop O: Potentially multiple variants in the range from pathogenic dbs with a pathogenic assertion (allow discordant for review purposes) | 1
Precalc functionality | Pathogenic variant database | get_pathogenic_variants_MVL I: chr, start, stop O: Potentially multiple variants in the range from MVL | 1
Precalc functionality | Predictions and computational | get_pdot I: vkey, transcript O: HGVS p. (via query of RVS) | 1
Precalc functionality | Predictions and computational | get_variant_type I: vkey, transcript O: variant type (stopgain, frameshift, CSS, stoploss, startloss, inframe, nonsynonymous, intronic) | 1
Precalc functionality | Predictions and computational | suggest_PVS1_PM4 I: VCF variant, transcript, phenotype_ID O: PVS1, PM4, PM4-S, PM4-VS, or other options | 1
Precalc functionality | Predictions and computational | get_valid_disease_variant_types I: phenotype_ID, transcript O: missense only/LOF only/any | 1
Precalc functionality | Predictions and computational | get_range_of_variant_codon I: VCF variant, transcript note: do math on refGene exons (unless way to use p.?) O: chr, start, stop | 1
Precalc functionality | Predictions and computational | get_range_of_new_stop_codon I: VCF variant, transcript note: for frameshift and stoploss... (and maybe CSS in the future if they decide to predict exon skipping) if p. annotation is consistently accurate, use that, in combination with get_range_of_variant_codon... (get variant's chr,pos get number of AA downstream to X [FS47X], math) consider pyhgvs_cdot_to_VCF if getting c. range for new stop is easy... else raw calc = this will need to take a (modified) cDNA sequence, translate it to find new stop codon, and return the chromosomal position of that new stop codon O: chr, start, stop | 2
Precalc functionality | Predictions and computational | is_NMD_predicted I: VCF variant, transcript O: yes or no | 1
Precalc functionality | Predictions and computational | get_cDNA_length I: transcript O: length in protein-coding bases (divide by 3 to get AA length) #beware stop codon inclusion | 1
Precalc functionality | Predictions and computational | get_length_of_cDNA_to_position I: chrom, pos, transcript O: length in protein-coding bases | 1
Precalc functionality | Predictions and computational | suggest_BP3 I: VCF variant note: for inframe, pos to pos + len(inframe) O: BP3, or other options | 1
Precalc functionality | Predictions and computational | suggest_PS1 I: VCF variant note: for inframe, pos to pos + len(inframe) O: PS1 or other options | 1
Precalc functionality | Predictions and computational | get_range_of_codon_with_consequence I: VCF variant note: returns interval of the codon affected (stopgain for FS) do math on refGene exons (unless way to use p.?) O: chr, start, stop | 1
Precalc functionality | Predictions and computational | affects_dispensable_exon I: chr, pos, transcript O: yes or no | 1
Precalc functionality | Predictions and computational | suggest_PP3_BP4_BP7 I: VCF variant, transcript O: PP3 , BP4, BP7, or other options | 1
Precalc functionality | Predictions and computational | get_dbscSNV_scores I: VCF variant O: ada_score, rf_score | 1
Precalc functionality | Predictions and computational | suggest_PP3_BP4_from_missense_predictors I: VCF variant O: PP3, BP4, null | 1
Precalc functionality | Predictions and computational | suggest_PP3_BP4_from_conservation I: VCF variant, transcript O: PP3, BP4, null | 1
Precalc functionality | Predictions and computational | suggest_PM5 I: VCF variant, transcript O: PM5 | 1
Precalc functionality | Predictions and computational | suggest_PM1 I: VCF variant, transcript O: PM1 | 1
Precalc functionality | Predictions and computational | suggest_PP2_BP1 I: VCF variant, transcript, phenotype O: PP2, BP1, or other options | 1
Additional VISta functionality | Final pathogenicity assertion | suggest_final_pathogenicity I: all assigned ACMG scores O: final pathogenicity assertion | 1
Additional VISta functionality | Variant and transcript interconversion and validation | cdot_to_VCF I: HGVS c. variant with or without transcript version O: left-normalized VCF (if no transcript version, assume most current) | 1 | Done (as python script at least, need to add to perl library)
Additional VISta functionality | Variant and transcript interconversion and validation | normalize_VCF_variant I: VCF variant O: left-normalized VCF variant |  | This functionality will be provided by Nick from RVS. Will import RVS module into VISta library and use his function
Additional VISta functionality | Variant and transcript interconversion and validation | get_vkey I: left-normalized VCF variant O: vkey
Additional VISta functionality | Variant and transcript interconversion and validation | get_all_cdot_and_pdot I: VCF variant O: all possible HGVS c. and p. for all refGene NM_ and NR_ transcripts (following performance assessment of SnpEff, Annovar, VEP, VAT) | 7
Additional VISta functionality | Variant and transcript interconversion and validation | check_for_cdot_and_pdot_discrepancies I: VCF variant, transcript O: A warning/notification that discrepancies are present if any HGVS c. or p. disagree (discrepancies will trigger manual review and correction of the official disease transcript c. and p. in RVS db) | 1
Additional VISta functionality | Supporting display planel / Variant browser | get_all_population_data I: vkey O: AC, AN, MAF, homo hetero hemiz counts for all available databases and ethnicities/sub-pops | 1
Additional VISta functionality | Supporting display planel / Variant browser | get_splice_site_coords I: chr, pos, transcript note: if variant is within 15bp of an exon, use that exon, else return null O: two intervals of chr:start-stop, one for donor and one for acceptor | 1
Additional VISta functionality | Supporting display planel / Variant browser | get_benign_variants I: chr, start, stop O: variants with MAF > (5% or disease AF?), and variants with concordant Ben or LBen assertions | 1
Additional VISta functionality | Supporting display planel / Variant browser | get_exon_number I: chr, pos, transcript note: if variant is within 15bp of an exon, use that exon, else return null O: exon number | 1
Additional VISta functionality | Supporting display planel / Variant browser | get_number_of_exons I: transcript O: number of exons | 1
Additional VISta functionality | Supporting display planel / Variant browser | is_first_donor_or_last_acceptor I: chr, pos, transcript O: first_donor, last_acceptor, or null | 1
Additional VISta functionality | Supporting display planel / Variant browser | get_protein_MSA I: chr:start-stop O: all alignments covering a position in the interval, or a subsection of the alignment if the interval is contained within a single alignment block (can neighboring blocks be separated by a GAP indicator ( maybe ¦), they are broken into different lines in UCSC)? Or can we just stick them next to each other ensuring the same species per row?) | 2
Additional VISta functionality | Supporting display planel / Variant browser | get_nucleotide_MSA I: chr:start-stop O: all alignments covering a position in the interval, or a subsection of the alignment if the interval is contained within a single alignment block (can neighboring blocks be separated by a GAP indicator ( maybe ¦), they are broken into different lines in UCSC)? Or can we just stick them next to each other ensuring the same species per row?) | 1
Additional VISta functionality | Supporting display planel / Variant browser | get_Alamut_scores I: VCF variant O: five scores from alamut | 3