## Sheet1
#Defining “precalculation” as just the functionality needed to suggest ACMG scores (remaining VISta functionality referred to as Additional VISta [Code/Functionality])
#Need to account not just for actual parsing but for formalizing the parsing into a script for future update use, maybe clarify which data sources this is even appropriate for beforehand (are there data sources where we agree the effort required to update won't be worth it)
#Comparing mockup and old precalc ideas for additional functions needed for supplemental display purposes
Source table prep or precalc code | Subarea | Task / Functionality of code needed | Time estimation in days | Status
Source table prep | Gene-phenotype information table | Overseeing manually curated disease-relevant transcript, disease allele frequency cutoff, inheritance pattern, can BS1 be applied (age of onset + penetrance)?, hotspot(PM1)-valid locations/patterns, and valid disease variant types (missense only/LOF only/any) |  | Template form still being designed
Source table prep | gnomAD coverage file | Prep for tabix usage (If we have concerns about data size storage, probably can be condensed into a reduced .bed format, collapse intervals with the same coverage, or limit to exons +100bp) | 1
Source table prep | HGVD | Multi-allelic sites if any need to be split into one variant per row Left normalize and generate vkey What % of sites are covered >20x on average? Remove sites below or remove individuals below and recalc AF? How many variants exist at an AF greater than observed in gnomAD? >1%? >5%? Convert to db format | 3
Source table prep | UK10K | Multi-allelic sites if any need to be split into one variant per row Left normalize and generate vkey What % of sites are covered >20x on average? Remove sites below or remove individuals below and recalc AF? How many variants exist at an AF greater than observed in gnomAD? >1%? >5%? Convert to db format | 3
Source table prep | Qatar sequencing study | The three files need to be merged and data adjusted accordingly Multi-allelic sites need to be split into one variant per row Left normalize and generate vkey What % of sites are covered >20x on average? Remove sites below or remove individuals below and recalc AF? How many variants exist at an AF greater than observed in gnomAD? >1%? >5%? Convert to db format | 3
Source table prep | Sema4's MVL | Remove duplicates, lift old transcripts to current, resolve any remaining vkey addition issues | 3
Source table prep | Emory's EmVClass | add vkey | 1
Source table prep | AmbryGenetics's AmbryShare | TBD
Source table prep | deafness variation database | add vkey | 1
Source table prep | CFTR france (875) | Copy-paste of nine pages or so (show 100 variants/page), more TBD after copy-paste (add vkey...) https://cftr.iurc.montp.inserm.fr/cgi-bin/variants.cgi?type=all& | 1
Source table prep | CFTR2 (326) | add vkey | 1
Source table prep | F11 | Needs to be parsed into table (currently quite messy), and vkey | 2
Source table prep | F9 | Needs to be parsed into table with one variant per row maintaining the order of patients, publications, and phenotype/functional information, and vkey added | 2
Source table prep | Infevers db | add vkey | 1
Source table prep | PAH db | Needs to be parsed into table (currently quite messy), and vkey | 2
Source table prep | ALPL db | add vkey | 1
Source table prep | ATP7B db | merge references table, add vkey | 1
Source table prep | COL7A1 db | convert data by patient to data by variant, maintain numbers, add vkey | 2
Source table prep | Pathogenic variant database | Determine final fields to be used for joined pathogenic variant database (maintain # pts and refs)
Source table prep | refGene | Finalize transcript table: 1 table with all transcript data present for searching (with date of most recent refGene table that was merged) -This table alone should never be used for variant lifting/validation -This table will be queried by various scripts to create temporary tables as needed for variant lifting/validation Script to download refGene updates, add version info, compare to transcript table, and merge updates | 2
Source table prep | dbNSFP | Compare, assess, determine cutoffs for REVEL, CADD, metaSVM vs SIFT, PolyPhen2, MutationTaster2 | 7
Source table prep | multiz100way | Parse into table with one human interval per row and each species's sequence is a column | 2
Source table prep | AA sub matrix (grantham / blossum ) | Compare, assess, determine substitution cutoffs for neutral vs damaging (maybe compare to our pathogenic missense variant db) | 7
Source table prep | uniprot | Need update from Nick - TBD dependent on form of downloaded data
Precalc functionality | Population data | get_highest_MAF I: VCF variant O: highest subpopulation/ethnicity MAF with AC > 2000 | 1
Precalc functionality | Population data | is_pos_covered I: Chromosomal position O: Is the position covered > 20x/sample on average? (yes or no) | 1
Precalc functionality | Population data | suggest_BA1_BS1_PM2 I: VCF variant O: BA1, BS1, PM2, or other options | 1
Precalc functionality | Population data | get_genotype_counts I: VCF variant O: genotype counts at this position (number homoz, hetero, hemiz) | 1
Precalc functionality | Population data | suggest_BS2 I: VCF variant O: BS2 or other options | 1
Precalc functionality | Pathogenic variant database | suggest_PP5_BP6 I: VCF variant, transcript O: PP5, BP6, or other options (concordant assertions, no publication references, not in MVL, compare get_patho to get_patho_MVL) | 1
Precalc functionality | Pathogenic variant database | get_pathogenic_variants I: chr, start, stop O: Variants from pathogenic db with a pathogenic assertion (allow discordant for review purposes) | 1
Precalc functionality | Pathogenic variant database | get_pathogenic_variants_MVL I: chr, start, stop O: Variants from pathogenic db with | 1
Precalc functionality | Pathogenic variant database | suggest_PS4 I: VCF variant, transcript O: PS4-M, PS4-P, or other options | 1
Precalc functionality | Predictions and computational | get_pdot I: VCF variant, transcript O: HGVS p. (via query of RVS db) | 1
Precalc functionality | Predictions and computational | get_variant_type I: VCF variant, transcript O: variant type (stopgain, frameshift, CSS, stoploss, startloss, inframe, nonsynonymous, intronic) | 1
Precalc functionality | Predictions and computational | suggest_PVS1_PM4 I: VCF variant, transcript, phenotype_ID O: PVS1, PM4, PM4-S, PM4-VS, or other options | 1
Precalc functionality | Predictions and computational | get_valid_disease_variant_types I: phenotype_ID, transcript O: missense only/LOF only/any | 1
Precalc functionality | Predictions and computational | get_range_of_variant_codon I: VCF variant, transcript note: do math on refGene exons (unless way to use p.?) O: chr, start, stop | 1
Precalc functionality | Predictions and computational | get_range_of_new_stop_codon I: VCF variant, transcript note: for frameshift and stoploss... if p. annotation is consistently accurate, use that, in combination with get_var_codon... consider pyhgvs_cdot_to_VCF if getting c. range for new stop is easy... else raw calc = this will need to take a (modified) cDNA sequence, translate it to find new stop codon, and return the chromosomal position of that new stop codon O: chr, start, stop | 2
Precalc functionality | Predictions and computational | is_NMD_predicted I: VCF variant, transcript O: yes or no | 1
Precalc functionality | Predictions and computational | get_cDNA_length I: transcript O: length in protein-coding bases (divide by 3 to get AA length) #beware stop codon inclusion | 1
Precalc functionality | Predictions and computational | get_length_of_cDNA_to_position I: chrom, pos, transcript O: length in protein-coding bases | 1
Precalc functionality | Predictions and computational | suggest_BP3 I: VCF variant note: for inframe, pos to pos + len(inframe) O: BP3, or other options | 1
Precalc functionality | Predictions and computational | suggest_PS1 I: VCF variant note: for inframe, pos to pos + len(inframe) O: PS1 or other options | 1
Precalc functionality | Predictions and computational | get_range_of_codon_with_consequence I: VCF variant note: returns interval of the codon affected (stopgain for FS) do math on refGene exons (unless way to use p.?) O: chr, start, stop | 1
Precalc functionality | Predictions and computational | affects_dispensable_exon I: chr, pos, transcript O: yes or no | 1
Precalc functionality | Predictions and computational | suggest_PP3_BP4_BP7 I: VCF variant, transcript O: PP3 , BP4, BP7, or other options | 1
Precalc functionality | Predictions and computational | get_ada_score I: VCF variant O: ada_score | 1
Precalc functionality | Predictions and computational | get_missense_predictor_results I: VCF variant O: PP3, BP4, null | 1
Precalc functionality | Predictions and computational | get_conservation_results I: VCF variant, transcript O: PP3, BP4, null | 1
Precalc functionality | Predictions and computational | suggest_PM5 I: VCF variant, transcript O: PP3 | 1
Precalc functionality | Predictions and computational | suggest_PM1 I: VCF variant, transcript O: PP3 | 1
Precalc functionality | Predictions and computational | suggest_PP2_BP1 I: VCF variant, transcript, phenotype O: PP2, BP1, or other options | 1
Additional VISta functionality | Final pathogenicity assertion | suggest_final_pathogenicity I: all assigned ACMG scores O: final pathogenicity assertion | 1
Additional VISta functionality | Variant and transcript interconversion and validation | cdot_to_VCF I: HGVS c. variant with or without transcript version O: left-normalized VCF (if no transcript version, assume most current) | 1 | Code written, Nick incorporating into RVS functionality, need to understand usage of RVS functions
Additional VISta functionality | Variant and transcript interconversion and validation | normalize_VCF I: VCF variant O: left-normalized VCF variant
Additional VISta functionality | Variant and transcript interconversion and validation | add_vkey I: left-normalized VCF variant O: vkey
Additional VISta functionality | Variant and transcript interconversion and validation | get_all_cdot_and_pdot I: VCF variant O: all possible HGVS c. and p. for all refGene NM_ and NR_ transcripts (following performance assessment of SnpEff, Annovar, VEP, VAT) | 7
Additional VISta functionality | Variant and transcript interconversion and validation | check_for_cdot_and_pdot_discrepancies I: VCF variant, transcript O: A warning/notification that discrepancies are present if any HGVS c. or p. disagree (discrepancies will trigger manual review and correction of the official disease transcript c. and p. in RVS db) | 1
Additional VISta functionality | Population data | get_all_MAF
Additional VISta functionality | Pathogenic variant database | get_benign_variants I: chr, start, stop O: variants with MAF > (5% or disease AF?), and variants with concordant Ben or LBen assertions
Additional VISta functionality
Additional VISta functionality
Additional VISta functionality
Additional VISta functionality